ATD San Diego Mentorship Program 2026: Roadmap & Timeline

This document outlines the roadmap and timeline for the 2026 ATD San Diego Mentorship Program. It is designed to be a comprehensive guide that incorporates lessons learned from the 2025 program and best practices in mentorship program design.

Program Goals

The 2026 program has the following key goals:

Goal

Target

Recruit mentor-mentee pairs

At least 10 pairs

Participant satisfaction

90%+ positive feedback on post-program survey

Attendance at cohort gatherings

80%+ average attendance

Budget

$700 or less

Program Phases

The 2026 program will be structured around five key phases, each with specific activities and deliverables.

Phase

Timeframe

Key Activities

Phase 1: Planning & Design

Dec 2025 - Jan 2026

Finalize program structure, timeline, and budget. Develop marketing materials.  Update and brand all 2025 items (surveys, program handbook, etc).

Begin recruiting and scheduling speakers

Create recruitment website

Develop support materials: Goal setting guide, Planning and conversation guide, Progress tracker, Meeting Agendas

Collaborate with Dir of Digital Experience and Dir of Technology to prepare marketing campaign

Supported by Deputy Director of Mentorship

(feedback, edits, other)

Phase 2: Recruitment & Application

Feb 2026

Launch marketing campaign, open applications, conduct outreach.

Phase 3: Matching & Onboarding

Mar 2026

Review applications, match pairs, conduct pre-kickoff training.

Phase 4: Program Execution

Apr - Jun 2026

Host kickoff and cohort gatherings, provide ongoing support.

Phase 5: Graduation & Evaluation

Jul 2026

Hold graduation event, collect feedback, conduct post-program analysis.

Detailed Timeline

Phase 1: Planning & Design (December 2025 - January 2026)

This phase focuses on laying the groundwork for a successful program. The Director of Mentorship will finalize the program structure, develop marketing materials, and secure the necessary resources.

Date

Activity

Owner

Notes

December 2025

Secure venue for in-person events

Chapter President

San Diego Humane Society

December 2025

Review 2025 program feedback and identify improvements

Director of Mentorship

Use survey data from 2025

January 2026

Finalize program structure and timeline

Director of Mentorship

This document

January 2026

Finalize budget and allocations

Director of Mentorship

$700 target

January - February 2026

Develop marketing materials (LinkedIn posts, website content)

Director of Digital Experience (Social media: assets and posts for chapter LinkedIn page and feed) —> Absorbed by Dir of Mentorship (Dir if Digital Exp to provide 4 graphics)

Director of Technology (Wild Apricot: repurpose assets used on social media for ATD homepage banner (changing the images for variety), place the 5 program meetings in the Wild Apricot event calendar)

Director of Mentorship (Design and build website for recruiting and program support)

See Marketing Strategy

Phase 2: Recruitment & Application (February - Early March 2026)

This phase focuses on attracting a diverse pool of mentors and mentees through a multi-channel marketing campaign.

Date

Activity

Owner

Notes

Week of Feb 1 (or 9, if can’t do WO Feb 1)

Launch LinkedIn marketing campaign

Director of Digital Experience -Social Media

Director of Technology - chapter homepage post?

Week 1: Promo video, announce applications are open

Two/three days later, share a promo image, remind applications open

Include links:

Mentee application

Mentor application

Recruitment website

Week of Feb 9 (and/or WO Feb 16)

Continue LinkedIn campaign

Director of Digital Experience-Social Media

Director of Technology - chapter homepage post?

Week 2: Mentee testimonials and a new promo image

Messaging focus: Applications are open (but closing Feb 28th)

Mentee application

Mentor application

Recruitment website

Week of Feb 16 (and/or WO Feb 23)

Continue LinkedIn campaign

Director of Digital Experience-Social Media

Director of Technology - chapter homepage post?

Week 3: Mentor testimonials and a new promo image

Announce: Applications due  this week - Feb 28th (This is the faux due date. Extend by one week next week)

Mentee application

Mentor application

Recruitment website

Week of Mar 2

Final recruitment push for applications

Director of Digital Experience-Social Media

Director of Technology - chapter homepage post?

Week 4: Extend the deadline and hype it

“Application deadline extended fir X more days! Don’t miss out! Application window closes March 7th!”

Mentee application

Mentor application

Recruitment website

Mar 7

Application deadline

Director of Mentorship

Close applications

Email all applicants with a Save-the-Date for the March 19th virtual training/orientation and meet/greet

Phase 3: Matching & Onboarding (March 2026)

This phase focuses on reviewing applications, matching mentor-mentee pairs, and preparing participants for the program.

Date

Activity

Owner

Notes

Mar 8 - 14

Review applications

Director of Mentorship

Supported by Deputy Director of Mentorship

Use matching survey data

Mar 8 - 14

Match mentor-mentee pairs

Director of Mentorship

Supported by Deputy Director of Mentorship

Reviewed and approved by ATD Board of Directors

Consider skills, goals, preferences

Mar 15

Notify participants of matches

Director of Mentorship

Send welcome email with match info

Mar 19

Pre-Kickoff Training (Virtual) | Mentee/Mentor Meet and Set Goals

Director of Mentorship

5:30 PM - 7:00 PM PST

Phase 4: Core Program Execution & Graduation (April–July 2026)

This phase is the heart of the program, where mentors and mentees meet regularly and attend cohort gatherings.

Date

Event

Format

Location

Time (PST)

Apr 1

Kickoff Event &

First Cohort Meeting

In-Person

San Diego Humane Society

5:30 PM - 7:30 PM

May 7

Cohort Meeting

In-Person

San Diego Humane Society

5:30 PM - 7:30 PM

Jun 4

Cohort Meeting

In-Person

San Diego Humane Society

5:30 PM - 7:30 PM

Jul 2

Cohort Meeting  & Graduation Event

In-Person

San Diego Humane Society

5:30 PM - 7:30 PM

Phase 5: Graduation & Evaluation (July–August 2026

This phase celebrates the achievements of the participants and gathers feedback for future program improvements.

Date

Activity

Owner

Notes

Jul 3 - 10

Send final program survey

Director of Mentorship

Gather feedback from all participants

Jul 15 - 31

Conduct post-program analysis

Director of Mentorship

Supported by Deputy Director of Mentorship

Summarize feedback, identify improvements for 2027

Budget Overview

The total budget for the 2026 program is $700, with a target spend of $600.

Category

Estimated Cost

Notes

Refreshments (4 events)

$400

$100 per event

Printed Materials

$50

Handbooks, name tags, etc.

Graduation Plaques/Items

Decorations

$150

Small thank-you gifts for speakers

Contingency

$100

For unexpected expenses

Total

$700