## Summary
DI Event Action List
Due Date | Action | Section | Responsible Party | Completed Y/N
2017-07-17 | Begin marketing campaign - mail promotional information & meet with business associates | Exhibit F
2017-08-17 | Request 90 minute complimentary program (in writing) | No. 20
2017-08-17 | Send to DI the number of registered participants - weekly | Exhibit F
2017-08-24 | Send to DI the number of registered participants - weekly | Exhibit F
2017-08-31 | Send to DI the number of registered participants - weekly | Exhibit F
2017-09-07 | Send to DI the number of registered participants - weekly | Exhibit F
2017-09-14 | Send to DI the number of registered participants - weekly | Exhibit F
2017-09-17 | Provide DI with a diagram of the event room/audio visual info/technical contact info | 4.8/Exhibit F
2017-09-17 | Travel expense reimbursement to DI is due | 4.11
2017-09-17 | Provide liability insurance certificate to DI | No. 10
2017-09-17 | Provide DI with boilerplate media release (approved by DI) for local newspapers and business journals | Exhibit F
2017-09-18 | Pay DI deposit of $22,500
2017-09-21 | Send to DI the number of registered participants - weekly
2017-09-24 | Begin publicity campaign with select newspapers, business journals, radio | Exhibit F
2017-09-28 | Send to DI the number of registered participants - weekly | Exhibit F
2017-10-01 | DI facilitators will contact ATD to walk thru program | Exhibit F
2017-10-05 | Send to DI the number of registered participants - weekly | Exhibit F
Oct 1 - 8 | DI ships materials to ATD (address?) | Exhibit F
2017-10-10 | Pay DI remaining balance of $22,500
2017-10-10 | Purchase ribbon for Mylar balloons | 4.9
2017-10-10 | Possible reimbursement to ATD for meals for DI presenters and complimentary program attendees
2017-10-12 | Send to DI the number of registered participants - weekly
2017-10-16 | Send to DI the final list of registration data | 4.6/Exhibit F
2017-10-16 | Conduct audio visual test on site and final room inspection | 4.9/Exhibit F
2017-10-16 | Fill 75 mylar balloons and attach ribbon | 4.9
2017-10-17 | Inform participants that there is no audio or video recording allowed. Announce this at the beginning of the event and maybe include it in a handout.
2017-10-17 | EVENT
2017-10-17 | At end of event, DI & ATD to sign & fax to DI "Confirmation of Program Attendance" | 4.6/Exhibit E & F
2017-10-18 | Forward names and emails for participants requesting CECs to DI | 4.12/Exhibit F
Press Releases
2017-06-05 | The Disney press release information was posted in the Rochester Community Lifestyles Newspaper this week.

## ProjTeamMeeting dates via phone
Meeting Dates
July (Mondays) | 2017-07-17 | Monday
| 2017-07-24 | Monday
| 2017-07-31 | Monday
August (Mondays and 1 Thursday) | 2017-08-07 | Monday
| 2017-08-14 | Monday
| 2017-08-21 | Monday
| 2017-08-28 | Monday
| 2017-08-31 | Thursday
September (Mondays and Fridays) | 2017-09-08 | Friday
| 2017-09-11 | Monday
| 2017-09-15 | Friday
| 2017-09-18 | Monday
| 2017-09-22 | Friday
| 2017-09-25 | Monday
| 2017-09-29 | Friday
October (Mondays and Fridays) | 2017-10-02 | Monday
| 2017-10-06 | Friday
| 2017-10-09 | Monday
| 2017-10-13 | Friday
| 2017-10-16 | Monday
EVENT | 2017-10-17