## Project Plan
Task | Status | Owner | Stage | Due date | Notes | TaskID
Form committees | Not started |  | Pre-event
Schedule bi weekly committee calls | Not started |  | Pre-event
Pick a date | Not started |  | Pre-event
Choose a theme | Not started |  | Pre-event
Decide on music | Not started |  | Pre-event
Choose a speaker | Not started |  | Pre-event
Decide on what to give as a speaker gift and amount | Not started |  | Pre-event
Purchase $50 Amazon for Keynote Speaker: Margaret Spence | Not started |  | Pre-event
Maintain constant contact with speaker | Not started |  | Day of
Pay Speaker | Not started |  | Post-event
Research venues | Not started |  | Pre-event
Analyze venue pricing and value | Not started |  | Pre-event
Create budget | Not started |  | Pre-event
Decide prices for attendance | Not started |  | Pre-event
Determine if there will be Best Practices prices | Not started |  | Pre-event
Test projectors with laptop (not at venue) | Not started
Check on card stock and document holders | Not started
Print certificates of all COL submissions | Not started
Secure a Submission Review Team (Judges) | Not started |  | Pre-event
Review previous 'rubric' for Submissions | Not started |  | Pre-event
Create marketing plan and graphics to solicit for Submissions | Not started |  | Pre-event
Determine how Submissions will be literally submitted (tech involved?) | Not started |  | Pre-event
Order Awards | Not started |  | Pre-event
Decide on Membership Packages | Not started |  | Pre-event
Solicit Sponsors | Not started |  | Pre-event
Brochure cards | Not started |  | Pre-event
Certificates & frames for submission in PDF for Barb to e-sign | Not started |  | Pre-event
Mic, speaker, screen | Not started
Ask ATDSFL Leadership and Influencers group to reach out to three potential Best Practice submissions | Not started |  | Pre-event

## Sponsorship Packages
Sponsorship Name | Amount | Event tickets Included | Hyperlinked Logo in Best Practice Booklet | Logo Included in (##) Emails | Use of Sponsor Logo Through the End of August 2025 | One Mailing List Use Through the End of August 2025 | Prominent 6’ Table Setup | Hyperlinked Logo on ATDSFL’s Website Through the End of August 2025 | Bar Table Setup (High top) | 3 minutes of microphone time for business promotion | 5 minutes of microphone time for business promotion | 12 Month Membership
Friend Sponsor | 0 | 1 | y | 2 | - | - | - | - | - | - |  | -
Harvest Sponsor | 0 | 1 | y | 2 | - | - | - | - | - | - |  | 1
Corporate Best Practice Sponsor | 0 | 1 | y | 5 | y | - | - | - | - | - |  | -
Selfie Station Sponsor* | 0 | 1 | y | 5 | y | y | - | - | y | - |  | -
Corporate Champion Sponsor | 0 | 2 | y | 8 | y | y | y | y |  | y |  | 1
Corporate Platinum Sponsor | 0 | 10 | y | 10 | y | y | y | y |  | - | y | 4
*one sponsorship opportunity available

## 2025 Sponsors
Company | Contact Name | Contact Email | Contact Phone | Sponsorship Level | Amount | Paid | Logo | Notes
[6 empty] | Paid | Sent
[6 empty] | Paid | Sent
[6 empty] | Paid | Sent
[6 empty] | Paid | Sent
[6 empty] | Paid | Sent
[6 empty] | Paid | Sent
[6 empty] | Paid | Sent
[6 empty] | Paid | Sent
[6 empty] | Paid | Sent
[6 empty] | Paid | Sent
[6 empty] | Paid | Sent

## COL Budget 2025
2025 Budget APPROVED as of DATE
Costs |  |  |  | Overall Profit/Loss (Budgeted) | 0
| Service Charge | 0% |  | Overall Profit/Loss (Actual) | 0
| Tax | 7% | exempt
| Per Person | #DIV/0!
|  | Budgeted |  | Actual |  |  |  |  | Budgeted |  | Actual
Expenses |  |  | 0 |  | 0 | Income |  |  |  | 0 |  | 0
[9 empty] | # | $
Dinner |  |  | 0 |  | 0 | Registration |  | Per | 0 | 0 | 0 | 0
| Catering Admin Fee | 0 |  |  |  |  | Member Early | 0 | 0 | 0 |  | 0
| Food & Beverage | 0 |  |  |  |  | Member Reg | 0 | 0 | 0 |  | 0
| AV | 0 |  |  |  |  | Member Late | 0 | 0 | 0 |  | 0
| Valet plus tax | 0 |  |  |  |  | Guest Early | 0 | 0 | 0 |  | 0
| Gratuity 22% | 0 |  |  |  |  | Guest Regular | 0 | 0 | 0 |  | 0
[7 empty] | Guest Late | 0 | 0 | 0 |  | 0
[7 empty] | Student Early | 0 | 0 | 0 |  | 0
[7 empty] | Student Reg | 0 | 0 | 0 |  | 0
[7 empty] | Student Late | 0 | 0 | 0 |  | 0
Awards | Awards company |  | 0 |  | 0 |  | Corporate Team Table: Member 5-9 | 0 | 0 | 0 |  | 0
| Frames/Certificates | 0 |  |  |  |  | Corporate Team Table: Guest 5-9 | 0 | 0 | 0 |  | 0
| Gold/Silver/Bronze | 0 |  |  |  |  | Corporate Team Table: Member 10+ | 0 | 0 | 0 |  | 0
[7 empty] | Corporate Team Table: Guest 10+ | 0 | 0 | 0 |  | 0
[7 empty] | Volunteers | 0 | 0 | 0 |  | 0
Best Practice Booklet/Giveaway |  |  | 0 |  | 0 |  | Sponsors | 0 | 0 | 0 |  | 0
| Flash drives | 0 |  |  |  |  | Friend of the Chapter Recipient | 0 | 0 | 0 |  | 0
| QR Brochure with printed card | 0 |  |  |  |  | Presenter | 0 | 0 | 0 |  | 0
| Sponsor Table cards | 0 |  |  |  |  | Pres Elect | 0 | 0 | 0 |  | 0
| Selfie Station |  | 0 |  | 0
| Decor | 0
Speaker Expenses Stipend |  |  | 0 |  | 0 | Qty Seats Comped - Sponsorship |  |  |  | 0 |  | 0
| Airfare | 0 |  |  |  | 1 | Friend Sponsor | 0 | 0 | 0 |  | 0
| Hotel | 0 |  | 0 |  | 1 | Friend Harvest Sponsor | 0 | 0 | 0 |  | 0
| Misc. Exp | 0 |  | 0 |  | 1 | Corporate Best Practice Sponsor | 0 | 0 | 0 |  | 0
[6 empty] | 1 | Selfie Station Sponsor* | 0 | 1 | 0 |  | 0
Judges Thank You |  |  | 0 |  | 0 | 2 | Corporate Champion Sponsor | 0 | 1 | 0 |  | 0
| Thank you | 0 |  |  |  | 10 | Corporate Platinum Sponsor | 0 | 0 | 0 |  | 0
Credit Card Processing Fees |  |  | 0 |  | 0
Registration: PayPal(#ppl80%)
Zelle
Sponsorship Expenses |  |  | 0 |  | 0
Prominent 6’ Table Setup
Bar Table Setup (High top)
Cost Per Attendee: |  |  | #DIV/0! | #DIV/0!

## Venue Options
Task | Status | Owner | Stage | Due date | Notes | Website and Info | ATDSFL File Link
| Not started |  | Pre-event
| In progress |  | Day of
| Completed |  | Post-event
| In progress |  | Pre-event
| Not started |  | Pre-event
| In progress |  | Pre-event
| In progress |  | Pre-event
| Completed |  | Pre-event
| In progress |  | Pre-event

## Previous Sponsors
Company | Status | Owner | Stage | Due date | Previous Sponsor Year & Info | Sponsorship Level | Contact | Phone | email | Notes
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| In progress |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event
| Not started |  | Pre-event

## Prospective Sponsors
Company | Status | Owner | Stage | Due date | Outreach Notes | Contact | Phone | Emails | Sponsorship Level | Invoice Sent Date | Invoice Paid Date

## Speaker List
Speaker | Fee | Status | Owner | Stage | Due date | Outreach Notes | Website | Vetting Notes | Phone | Email

## old COLD Budget (hidden)
Champions of Learning 2025 Budget
Revenue
Expenses
Total
Goal number of Paid Participants |  | 80 |  |  | Actual number of Paid Participants
Goal Sponsorships |  | #NAME? |  |  | Actual Sponsorships
Total proposed budget |  | 6645 |  |  | Total actual event cost
Goal Cost per person |  | #NAME? |  |  | Actual Cost per person | #DIV/0!
Expenses |  |  |  | Revenue
[6 empty] | Rate | # | $
Food and Venue |  | 5210 |  | Registration Rates
NOTE: Must include parking | Deposit | 0 |  |  | Member Early (Includes Sister Chapter/Member/Corporate Member/Corporate Guest/Sponsor Guest/COL Submitter and Guest) | 50 |  | 0
Tables of 10 | Food and Beverage Expenses | 3000 |  |  | Member Regular (Includes Sister Chapter/Member/Corporate Member/Corporate Guest/Sponsor Guest/COL Submitter) | 55 |  | 0
Asked for small table next to podium, also needed table for tech | Gratuity | 240 |  |  | Member Late (Includes Sister Chapter/Member/Corporate Member/Corporate Guest/COL Submitter/Sponsor Guest/Student) | 60 |  | 0
| Bartender, tip, one drink ticket | 475 |  |  | Student Member (Early and Regular) | 40 |  | 0
| Room Charge | 500 |  |  | Student Late (Early and Regular) | 45 |  | 0
| AV - includes 2 tables, added 2 more tables, wireless microphone/podium , projector, screen | 150 |  |  | Guest (Early) | 55 |  | 0
| Service Charge (20% gratuity) - make sure this includes tip | 845 |  |  | Guest (Regular) | 65 |  | 0
| Tax 7% | 0 |  |  | Guest (Late) | 75 |  | 0
[5 empty] | Corporate Team Member Add-On | 40 |  | 0
[5 empty] | Corporate Team Non-Member Add-On | 50 |  | 0
Best Practice Awards | Total | 180 |  |  | Corporate Team Special: 5 or More Member | 200 |  | 0
| Certificate Paper | 10 |  |  | Corporate Team Special: 5 or More Guest | 250 |  | 0
| Awards | 150 |  |  | Proposed: ATDSFL COL Volunteer Rate Max. 5 | 45
| Frames | 20 |  | Comps/Sponsors |  |  | 0 | 0
Comps/Sponsors
Speaker | Total | 750 |  |  | Presenter and Guest | 0 | 2 | 0
| Speaker - flat stipend | 750 |  |  | President-Elect | 0 | 1 | 0
[5 empty] | Event Sponsor | 1000 | 1 | #NAME?
Sponsor Expenses | Total | 200 |  |  | Friend Sponsor | 200 | 7 | #NAME?
| Printed Mini Brochure with QR Codes/Sponsor Promos | 200 |  |  | Selfie Station Sponsor | 500 | 1 | #NAME?
[5 empty] | Best Practice Sponsor | 750 | 1 | #NAME?
Misc Expenses | Total | 120 |  |  | Happy Hour Sponsor | 750 | 1 | #NAME?
| Card | 5 |  |  | Premier Sponsor | 1000 | 1 | #NAME?
| Placemats | 15 |  |  | Total Proposed Sponsorss |  |  | #NAME?
| Selfie Station | 100
Refunds and PayPal Fees | Total | 185
| Registration: PayPal Fees | 80
| Sponsorship: PayPal Fees | 55
| Refunds | 50
Total Expenses |  | 6645
Sponsorship | (Proposed) | Goal | Fee
Required | Friend Sponsor (up to 10) | 7 | 200
Registration | 1 comp registration
Hyperlinked Logo | On Event page, included in mini Best Practice Booklet wtih linked QR Code
Logo | Select Emails
Required | Selfie Station Sponsors (up tp 1) | 1 | 500
Setup | Bar Table Setup
Registration | 1 comp registration
Hyperlinked Logo | On Event page, included in mini Best Practice Booklet wtih linked QR Code
Logo | Select Emails
Sponor Logo | Use of ATD South Florida Sponor Logo for you to proudly display on website through June 30, 2024
Optional - One Drink | Happy Hour Sponsor (up to 2) | 2 | 750
Setup | Bar Table Setup
Registration | 1 comp registration
Hyperlinked Logo | On Event page, included in mini Best Practice Booklet wtih linked QR Code
Logo | Select Emails
Sponor Logo | Use of ATD South Florida Sponor Logo for you to proudly display on website through June 30, 2024
Mailing List | One-time mailing list use before June 30, 2024
Optional - Brochure | Best Practice Sponsor (1) | 2 | 750
Setup | Prominent 6' Table Setup
Registration | 1 comp registration
Hyperlinked Logo | On Event page, included in mini Best Practice Booklet wtih linked QR Code
Logo | Select Emails
Sponor Logo | Use of ATD South Florida Sponor Logo for you to proudly display on website through June 30, 2024
Mailing List | One-time mailing list use before June 30, 2024
Required | Premiere Sponsor (up to 3) | 1 | 1000
Setup | Prominent 6' Table Setup
Registration | 2 comp registration
Hyperlinked Logo | On Event page, included in mini Best Practice Booklet wtih linked QR Code
Logo | Select Emails
Sponor Logo | Use of ATD South Florida Sponor Logo for you to proudly display on website through June 30, 2024
Mailing List | One-time mailing list use before June 30, 2024
Mic Time | 3 min microphine time for business promotion
Website | Hyperlinked logo on webiste through June 30, 2024
In Kind Agreemant with Sixt for Toy Drive |  | 0 | 0
| Total Sponsorship Budgeted | 6